## Лист1
Telecommunication：
| Item | Question | Answer
|  | 1. Telecommunication equipment is requested in RfQ. What should be done if there is any existing modern telecommunication equipment? | The existing equipment, which will not use and wll hamper to installation of new equipment, should be dismantled.
2. Telecontrol (page 310)
|  | If signals, commands and measurements are transferred via gateways, no RTUs are needed, can you confirm? Do you require FO patchpanels as well? | Old RTUs also are aneccessary with their all trasndussers and signals, for the remote control via relay.
|  | 3. Please provide the following documentation for each subsation . | It is attached
|  | 1.Please define the scope of telecommunication work about the four substations of this project clearly. | All MP relays should be provided with optical outputs/ inputs. The telecommunication should be implemented via optical cables and PLC.
|  | 2.Please provide the figure of grid telecommunication status quo related to this project. | The drawing is attached .
|  | 3.Provide the existing drawing of power line carrier channels and fiber optic communication channels in four substations of this project, including model of power line carrier equipment，SDH equipment and PCM Access multiplexers. | We will inform you later
|  | 4.Provide the technical schedules of telecommunication equipment. | Will be provided later
Employer requirements page 360 | Point 1.1.13.9.9 6 kV equipment technical data sheet … and its RTU equipment ….. | At SS Vanadzor 1 there are no RTU. Please clarify. | In Charentsavan-3, Vanadzor 1 substations there are no RTU. But it is necessary to foreseen Gateways.
Employer requirements page 362 | Point 1.0.13.12.2 ( point should be 1.1.13.12.2) Telecommunication | All three points equipments are not installed at SS Vanadzor 1. Please clarify. | It is necessary to foreseen Gateways.
| Question N 34 in pre-bid meeting | Should the PLCs be replaced or not , if they should, it is necessary to provide their technical documents. | PLC –ները չեն փոխարինվում: Փաստաթղթերը կտրամադրվեն հետագայում
| Question N 37 in pre-bid meeting | Will the remote control devices be changed or they are remaining the same. | PLC should remain, but relays should have optical inputs/output to send/receive the signals.
| Question N 40 in pre-bid meeting | The connection between the substations will be implemented via optical fiber cables. Will it be required only connection links or the cables supply is needed too. | It is necessary to supply the cables also.
| Section IV Bidding forms Existing and new RTU for Haghtanak and Ashnak | According to the tender the existing RTU has to be reconnected to the new HV equipment and in addition a new RTU / Gateway has to be provided. We have two questions: Can the gateway / RTU of the new DCS be used as the new RTU described in 1.2.4.6.3? The new RTU will be supplied and therefore we kindly ask to remove the existing RTU and replace it through the requested new one, as the costs for the customer are lower in this case. | No
| 1. Scope of Supply of Plant and Installation Services by the Contractor '1.1.6.4.3. page 310 existing SCADA | Please clarify which is the mentioned existing SCADA (RCC, load dispatch center)? How many SCADA connections are requested from each gateway? | Enegy power system Operator has SCADA system via which it can receive information from all energy objects. It should be foreseen the connection of mini SCADA to the Operator's SCADA system , in order to receive neccessary information.